Response Team Incident Action Plan

Confidential – Internal Incident Communication

| Audience | Response Team: IT, Development, QA, Project Management, Legal, Client Services, HR |
| --- | --- |
| From | IT Operations Manager |
| Date | June 2, 2026 |
| Subject | Plan to resolve the critical scheduling update error |
| Scenario | Scenario 2: Critical Error |

# Purpose and Current Status

This plan coordinates the cross-functional response to the critical scheduling update error. The flawed build could permit unlimited services instead of the contracted one service per purchase. The root cause is a process-compliance failure: one developer commit was not reviewed, and QA sign-off was bypassed for 12 modules. The defect was found four days after staging deployment, before the scheduled client production release (Western Governors University [WGU], n.d.).

Our objective is to prevent production deployment of the flawed build, correct and retest the affected code, prepare a controlled client communication plan, and put preventive controls in place so a QA bypass cannot recur.

# Incident Response Priorities

- Protect the client from a faulty production release and the related first-30-day revenue exposure.

- Hit a realistic corrected-release window of about 12 days after incident confirmation.

- Maintain one source of truth for status, risks, blockers, and client-facing information.

- Capture lessons learned without blame so the team can strengthen release controls.

Figure 1. Response team critical path. The dashed line marks the contract deadline on Day 7; the corrective release follows full QA sign-off in the Day 12–14 window.

# Roles and Responsibilities

| Function | Primary responsibility | Key task | Update cadence |
| --- | --- | --- | --- |
| IT Operations | Containment and release control | Freeze promotion of the flawed build, manage rollback, and coordinate operational readiness. | Twice daily until rollback complete; daily after. |
| Development Lead | Code remediation | Fix the scheduling-limit logic and verify peer review of the originally unreviewed commit. | Daily by 4 p.m. |
| QA Lead | Testing and sign-off | Retest all 12 bypassed modules and confirm 100% QA compliance before release. | Daily by 4 p.m. |
| Project Management | Schedule and dependencies | Own the incident timeline, blockers, staffing needs, and release-readiness checklist. | Daily status report. |
| Legal | Contract and risk review | Assess SLA exposure and review all client-facing language before it is sent. | As needed; required before client messages. |
| Client Services / Account Mgr. | Client communication | Prepare status updates, the expected delivery window, and the support-readiness plan. | Daily client-ready update. |
| HR | People and process support | Support coaching, policy reinforcement, and a non-punitive post-incident learning process. | Postmortem and follow-up. |

# Execution Process

Day 0–2 – Containment: freeze the flawed build, roll back the staging artifact from the release path, and document the affected modules.

Day 1–6 – Remediation: Development corrects the scheduling authorization logic and completes peer review before QA intake.

Day 5–12 – QA retesting: QA completes regression testing and validates that one purchase permits only one service.

Day 10–12 – Release readiness: Project Management confirms checklist completion; Legal and Client Services approve client-facing messaging.

Day 12–14 – Post-incident review: the team reviews root cause, control gaps, and prevention actions, focusing on process improvement rather than individual blame.

# Open Dialogue and Lessons Learned

Every function should raise risks, blockers, and control gaps immediately. The post-incident discussion should answer three questions: where did the release process allow a QA bypass, what automation or approval gate would have stopped it, and what training or documentation change would help the team avoid a repeat.

# Prevention Targets

- Zero QA bypasses for release-bound code, with 100% QA-check compliance required before any production promotion.

- Automated code-review coverage for 90% of new commits by Q3.

- Annual prevention budget of about $250,000 for tooling and training, justified against the potential loss of a single $500,000 client contract.

- Post-release monitoring of scheduling anomalies and client-complaint trends during the first week after the corrective release.

## References

Western Governors University. (n.d.). E011.1 Technical communication: Scenario 2 – Critical error [Course scenario].